{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["ЗАТО Заозерск"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"ЗАТО Заозерск","index":0,"n_rows":20,"n_cols":8,"rows_kept":20,"cut":false,"hidden":false,"merged":[[18,0,18,7],[19,0,19,7],[0,0,0,7],[1,0,1,3],[1,6,1,7],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,3,7]],"flags":["formulas_cached_only"]}
["План выполнения ямочного ремонта"]
["Проведение ямочного ремонта",null,null,null,"отчет актуален на дату:","06/11/2020","исп. Васютичев Н.В. тел (815-56)3-13-89, моб. 911-339-99-94, e-mail: mku-ugh@mail.ru"]
[]
["Адрес","Количество ям на участке (адресе), ед","План, кв.м","Факт, кв.м","% выполнения","Метод устранения дефекта (горячей АБС, холодный асфальт, и т.п.)","Дата проведения ямочного ремонта на объекте"]
[{"$nulls":6},"план ","факт"]
["ЗАТО Заозерск  ИТОГО, в т.ч.",null,2000,794,null,"Холодный"]
["ул.Лен.Комсомола",null,80,80,100,"Холодный","12-18.05.20","2020-06-01"]
["Мост через реку Западная Лица",null,55,40,73,"Холодный","18-20.05.20"]
["ул.Колышкина",null,40,40,100,"Холодный","20-27.05.20","2020-05-27"]
["ул.Флотская",null,120,null,null,"Холодный","27-29.05.20"]
["ул.Строительная",null,90,null,null,"Холодный","01-03.06.20"]
["ул.Мира",null,130,null,null,"Холодный","03-05.06.20"]
["ул.Г.Чумаченко",null,120,null,null,"Холодный","08-10.06.20"]
["ул.М.Рябинина",null,140,null,null,"Холодный","10-11.06.20"]
["пер.Молодежный",null,75,null,null,"Холодный","2020-06-11"]
["пер.Гранитный",null,50,null,null,"Холодный","2020-06-12"]
["гб. Большая Лопаткина",null,600,234,39,"Холодный","01.06 - 30.06.20"]
["гб.Нерпичья",null,500,400,80,"Холодный","01.06 - 30.06.20"]
["Работы не проводились из-за погодных условий (дожди)"]
["* Даты выполнения ямочного ремонта могут быть изменены в связи с погодными условиями, и устранением замечаний по предписаниям."]